## Sheet1
Day | Focus | Tasks
Day 1–2 | Finalize & Prepare | - Create block diagram (draw.io/PowerPoint) - Confirm hardware availability (ESP32, Load Cell, Servo, GSM/Fingerprint) - Decide OTP vs Fingerprint
Day 3–4 | Hardware Testing | - Test Servo Motor (simple rotation) - Test Load Cell + HX711 (show readings) - Optional: Servo triggers on weight threshold
Day 5 | Authentication + Data Logging | - Set up OTP (GSM) or Fingerprint sensor (R305) - Test Google Sheets / Firebase logging - Fallback: Save to CSV
Day 6 | Subsystem Integration | - Integrate Load Cell + Servo for dispensing - Log transactions (Quantity + ID + Fraud flag) - Basic fraud detection (Claimed > Limit)
Day 7 | Demo Prep | - Prepare PPT (Problem, Architecture, Hardware, Progress) - Add demo pics/videos - Practice explanation flow